## Sheet1
Deliverable | Due Date | Status | Lead | Others
Product Description | 2016-09-02 | Submitted
BB Schematic | 2016-09-08 | Submitted | Daniel | Kyle
BB Layout | 2016-09-14 | Submitted | Daniel | Kyle
RRC Table | 2016-09-20 | completed | Cassandra
Level 1 FD | 2016-09-20 | Completed | Cassandra
System Diagram | 2016-09-20 | Completed | Hassan
BB Final Layout | 2016-09-22 | completed | Daniel | Kyle
UROP Props | 2016-09-27 | N/A
L2 FD | 2016-09-29 | complete | cassandra
EEF Props | 2016-10-04 | complete
BB Demos | 2016-10-11 | complete
BB Demos | 2016-10-13 | complete
PDR | 2016-10-18 | complete
PDR | 2016-10-19 | complete
PDR | 2016-10-20 | complete
PDR Docs | 2016-10-27 | complete
Draft POC | 2016-11-03 | complete
Final POC | 2016-11-10 | complete | Cassandra | Daniel
POC Demo | 2016-11-29
POC Demo | 2016-12-01
POC Demo | 2016-12-06
POC Demo | 2016-12-08
Draft CDR | 2017-01-24
CDR | 2017-01-31
CDR | 2017-02-01
CDR | 2017-02-02
Expo | 2017-05-04